## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 40 | 25-003 | MULLIS STREET PEDESTRIAN IMPROVEMENTS PROJECT | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Fairburn | Construction | The installation of a 5-foot concrete sidewalk with a 2-foot beauty strip along Mullis Street, from West Campbellton Street to Dodd Street, and from Dodd Street to Strickland Street. The project also entails the installation of pedestrian improvements on a section of Dodd Street, from Mullis Street to W. Broad Street. The work includes the removal of existing curb & gutter and header curb, and the installation of new header curb and sidewalk. This contract will also include preparation of sub-grade, saw-cutting and demolition of existing asphalt as well as clean up and backfilling. The scope of Add Alternate #1 consists of the installation of pedestrian lighting | CONSTRUCTION 57 INC. | POND ENGINEERING | March, 2025 | May, 2025 | July, 2025 | June, 2025 |  | Sales Tax | $570,201 | $570,201 | $0 | Green | Green | Active | anthony.belcher@fairburn.com | 2025 | 2025-05-06 10:21:42 | GA |  | 2025-05-06
[17 empty] | SUM = 570,201 | SUM = 570,201 | SUM = 0