## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 76 | S2185-1 | Lake Forrest Sidewalk Phase 1 | Tier 1 | Pedestrian and Bike Improvements | TSPLOST2 | Sandy Springs | Completed | Lake Forest Sidewalk from south of Pine Lake Drive to Mt Paran Road | Excellere | Kimley Horn | March, 2025 | January, 2023 | December, 2025 | December, 2025 |  | Sales Tax | $272,700 | $269,918 | $2,782 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2025 | 2026-03-06 15:44:29
[17 empty] | SUM = 272,700 | SUM = 269,918 | SUM = 2,782