## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ROS- 3 |  | Oxbo Road at SR9 Intersection Improvement | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Construction | Redesign of the intersection of Oxbo Road and SR 9 creating a full intersection and adding a new traffic signal. The new intersection will be rebuilt just south of the existing SR 9 at Oxbo Road intersection. The project also extends Oxbo Road west to connect directly to Mimosa Blvd which provides connectivity. The project also will link Oxbo Road to Pleasant Hill Street and Elm Streets. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. | ER Snell | Clark Patterson Lee, Inc. | June, 2019 | November, 2019 | December, 2022 | December, 2022 | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $12,500,000 | $11,620,368 | $879,632 | Red | Red | Active | dcox@roswellgov.com |  | 2023-04-14 16:17:38
[17 empty] | SUM = 12,500,000 | SUM = 11,620,368 | SUM = 879,632