## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ROS- 5 |  | Rucker Road Complete Street | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Roswell | Completed | Reconstruction of Rucker Road from Roswell/Alpharetta City Limit boundary to GA-140/Arnold Mill Road/Houze Road Intersection. The project will include the addition of a multi-use path and sidewalk enhancements. Funding spent may include funds paid to contractors/consultants or indicate encumbered funds set aside for future payments. | CW Matthews | TY Lynn | December, 2018 | March, 2019 | April, 2021 | April, 2021 | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $2,264,327 | $2,090,663 | $173,664 | Red | Green | Active | dcox@roswellgov.com |  | 2023-04-14 16:18:26
[17 empty] | SUM = 2,264,327 | SUM = 2,090,663 | SUM = 173,664