## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ROS- 6 |  | Holcomb Bridge Interchange | Tier 1 | Operation and Safety Improvements | TSPLOST | Roswell | Planning | Design for projects from the Holcomb Bridge Road Corridor Study, possibly including reconstruction of the bridges or ramps at the GA-400 interchange at Holcomb Bridge Road. Roswell has partnered with GDOT to help provide TSPLOST funding for the Holcomb Bridge Road interchange within Roswell as part of their GA-400 Express Lane project. The funding is being used to fund additional improvements and have GDOT reconstruct the existing interchange at Holcomb Bridge Road. In summer of 2021, GDOT announced they would be revisiting their GA-400 Express Lane project's schedule as construction bids at that time were not accepted. As this project is tied to GDOT's project timeline, Roswell is continuing to coordinate with GDOT on their plans moving forward regarding their GA-400 Express Lane project. | [6 empty] | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $6,000,000 | $0 | $6,000,000 | Gray | Gray | Active | dcox@roswellgov.com |  | 2023-04-14 16:18:44
[17 empty] | SUM = 6,000,000 | SUM = 0 | SUM = 6,000,000