## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
ROS- 7 |  | Old Holcomb Bridge Road Bridge Replacement | Tier 1 | Bridges | TSPLOST | Roswell | Planning | This project is the anticipated replacement of weight-restricted bridge on Old Holcomb Bridge Road bridge over Big Creek. This project's scope has been merged into the work scope of the Big Creek Parkway project. Construction along Old Holcomb Bridge Road (as part of the Big Creek Parkway project) is anticipated to begin in 2022. |  | In House |  |  |  |  | https://www.roswellgov.com/government/departments/transportation/t-splost-projects | Sales Tax | $3,086,390 | $24,975 | $3,061,415 | Green | Green | Active | dcox@roswellgov.com |  | 2023-04-14 16:19:02
[17 empty] | SUM = 3,086,390 | SUM = 24,975 | SUM = 3,061,415