## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 11 | TS105 | Roswell Road at Grogans Ferry Road | Tier 1 | Operation and Safety Improvements | TSPLOST | Sandy Springs | Completed | Realignment of the intersection and installation of traffic signal. Access management on Roswell Road. | Ohmshiv | Columbia Engnieering | July, 2020 | February, 2018 | April, 2023 | March, 2023 | https://www.sandyspringsga.gov/roswell-roadgrogans-ferry-road-improvements | Sales Tax | $4,800,000 | $4,765,529 | $34,471 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2024-03-29 14:31:48
[17 empty] | SUM = 4,800,000 | SUM = 4,765,529 | SUM = 34,471