## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 3 | 17-005 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | City-Wide Resurfacing. The project includes milling, temporary traffic control, asphalt paving, thermoplastic striping, manhole adjustments and associated tasks. Our strategy was to use 2017-2018 TSPLOST funds to focus our resurfacing efforts on the heart of the City (downtown) and extend future efforts to its extremities. In doing so, the implementation of the Downtown LCI Project, would have a more meaningful impact on the revitalization of FairburnÆs Historic Downtown. | E.R. Snell Contractor, Inc. | In-House | June, 2017 | November, 2017 | December, 2018 | October, 2018 |  | Sales Tax | $1,200,000 | $968,367 | $231,633 | Green | Green | Active | lthompson@fairburn.com | 2017
[17 empty] | SUM = 1,200,000 | SUM = 968,367 | SUM = 231,633