## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 16 | TS131 | Peachtree Dunwoody Multi-Use Path | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Land | The project consists of a multi-use path from Hammond Drive to Abernathy Road in conjunction with PCID. |  | Kimley Horn | October, 2026 | January, 2024 | April, 2028 | April, 2028 |  | Sales Tax | $3,050,000 | $465,721 | $2,584,279 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2028 | 2026-03-06 15:48:32
[17 empty] | SUM = 3,050,000 | SUM = 465,721 | SUM = 2,584,279