## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 17 | TS136 | Central Parkway Sidewalk Gap Fill | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Provided a 600 ft. sidewalk gap fill in Sandy Springs and Dunwoody along Central Parkway in the Perimeter district | GDP | PCID/Dunwoody | February, 2018 | March, 2018 | March, 2018 | March, 2018 |  | Sales Tax | $15,899 | $15,899 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2018 | 2021-05-04 19:12:29
[17 empty] | SUM = 15,899 | SUM = 15,899 | SUM = 0