## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 19 | TS192 | Mt. Vernon Multi Use Path | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Construction | Multi-modal transportation options are being considered in this key link between City Springs and the Sandy Springs MARTA Station | Excellere | KCI | December, 2022 | July, 2017 | April, 2026 | April, 2026 | http://spr.gs/mvc | Sales Tax | $18,075,160 | $14,383,687 | $3,691,473 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2026 | 2026-03-06 15:49:30
[17 empty] | SUM = 18,075,160 | SUM = 14,383,687 | SUM = 3,691,473