## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 23 | TS137 | Johnson Ferry Road - Glenridge Connector to existing sidewalk at Wells Fargo site | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidepath system on south side of Johnson Ferry Road from existing sidewalk onto Glenridge Drive | Proterra Development | AEI | May, 2019 | May, 2017 | October, 2020 | September, 2020 |  | Sales Tax | $472,581 | $472,581 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2020 | 2022-08-16 13:17:02
[17 empty] | SUM = 472,581 | SUM = 472,581 | SUM = 0