## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 25 | TS165 | Northwood Drive - Kingsport to Roswell Road | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on south side of Northwood Drive from Kingsport Dr. to existing sidewalk | Proterra Development | AEI | May, 2018 | July, 2018 | February, 2019 | December, 2018 |  | Sales Tax | $268,968 | $268,968 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2019 | 2022-05-26 18:05:34
[17 empty] | SUM = 268,968 | SUM = 268,968 | SUM = 0