## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 26 | TS166 | Spalding Drive - Spalding Lake Ct. to Holcomb Bridge | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | The City included adding multi-use paths along Spalding Drive as part of the T-SPLOST project. As part of the agreement with Gwinnett County, improvements will include a multi-use path along the south side of Spalding Drive, from Winters Chapel Road to River Exchange Drive, and a sidewalk on the north side of Spalding Drive from Winters Chapel Road to River Exchange Drive. The sidewalks will connect to the existing sidewalks on Holcomb Bridge Road and will provide enhanced connectivity to Crooked Creek Park and the surrounding neighborhoods. | CMES | Atkins | December, 2019 | October, 2017 | May, 2023 | May, 2023 | http://spr.gs/spalding | Sales Tax | $1,963,352 | $1,882,608 | $80,744 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2023-12-14 15:54:36
[17 empty] | SUM = 1,963,352 | SUM = 1,882,608 | SUM = 80,744