## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 28 | TS168 | Dalrymple Road - existing sidewalk at Princeton Sq (@Princeton Way) to Duncourtney Dr. | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on north side of Dalrymple Road from Princeton Way to Duncourtney Dr. May need mid-block crossing at Duncourtney Dr to the existing sidewalk on south side | Construction 57 | KCI | September, 2021 | February, 2020 | April, 2023 | March, 2023 |  | Sales Tax | $759,155 | $426,265 | $332,890 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2023 | 2023-04-27 13:47:17
[17 empty] | SUM = 759,155 | SUM = 426,265 | SUM = 332,890