## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 29 | TS169 | Dunwoody Club Dr. - Spalding to exsiting walk at Fenimore Circle | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Dunwoody Club Drive from existing sidewalk to Spalding Dr | CMES | Calyx | July, 2020 | March, 2019 | May, 2022 | May, 2022 |  | Sales Tax | $1,165,000 | $1,036,283 | $128,717 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2022 | 2023-01-27 22:08:43
[17 empty] | SUM = 1,165,000 | SUM = 1,036,283 | SUM = 128,717