## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 30 | TS170 | Interstate North Pkwy - Chattahoochee River to Northside Drive | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Sidepath system on north side of Interstate Pkwy from the park to Northside Drive | CMES | Atkins | October, 2020 | March, 2019 | November, 2022 | November, 2022 |  | Sales Tax | $2,646,272 | $2,436,362 | $209,910 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2022 | 2023-01-27 22:10:38
[17 empty] | SUM = 2,646,272 | SUM = 2,436,362 | SUM = 209,910