## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CSS- 31 | TS171 | Roberts Drive (Ex. Walk S of Northridge Rd to Ex. Walk at Davis Academy) | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Sandy Springs | Completed | Connect the sidewalk system on east side of Roberts Drive from Northridge to Davis Academy | SD&C | Calyx | July, 2020 | February, 2019 | January, 2022 | July, 2021 |  | Sales Tax | $446,377 | $446,377 | $0 | Green | Green | Active | ajohnson@sandyspringsga.gov | 2021 | 2022-07-29 18:04:05
[17 empty] | SUM = 446,377 | SUM = 446,377 | SUM = 0