## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 2 | CH-101 | Rico Road Part A Maintenance and Improvements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Completed | The project consists of Hot Mix Asphalt (HMA) patching, HMA leveling, HMA topping, striping, shoulder building, and grassing on 1.4 miles of Rico Road beginning at South Fulton Parkway and ending at Campbellton Redwine Road. | ER Snell |  | August, 2017 | September, 2017 | December, 2017 | December, 2017 |  | Sales Tax | $304,770 | $301,469 | $3,301 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2017 | 2021-12-13 18:29:50
[17 empty] | SUM = 304,770 | SUM = 301,469 | SUM = 3,301