## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 3 | CH-102 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Chattahoochee Hills | Completed | Location #1 û Wilkerson Mill Road: This portion of the project consists of Hot Mix Asphalt (HMA) patching, HMA leveling, HMA topping, striping, raised pavement markers, shoulder building, and grassing on approx. 2.5 miles of Wilkerson Mill Road beginning at Cochran Mill Road and ending at Cascade Palmetto Highway. Location #2 û Atlanta Newnan Road: This portion of the project consists of Full Depth Reclamation of the existing road bed, HMA binder and topping course, shoulder building, grassing, striping and raised pavement markers on 1.5 miles of roadway beginning at Hutcheson Ferry Road and ending at the bridge at the Coweta County line. | Atlanta Paving | DWS | September, 2018 | October, 2018 | December, 2018 | February, 2019 |  | $470,233 TSPLOST & $663,154 Capital Fund | $1,176,646 | $1,133,387 | $43,259 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2018-2019 | 2021-12-13 18:30:01
[17 empty] | SUM = 1,176,646 | SUM = 1,133,387 | SUM = 43,259