## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 11 | EP-179 | Headland and Delowe Intersection | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | East Point | Completed | Pedestrian/Bike/Landscape/Streetscape Projects in City of East Point - Delowe Drive (Washington Rd to SR 166) The last phase of the project included in the Delowe Drive / Headland Drive Intersection Upgrade. |  | Foresite Group | March, 2021 | January, 2022 | December, 2021 | November, 2021 |  | Sales Tax | $1,122,644 | $825,000 | $297,644 | Green | Green | Active | chall@eastpointcity.org | 2021 | 2024-11-07 14:45:56
[17 empty] | SUM = 1,122,644 | SUM = 825,000 | SUM = 297,644