## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 13 | EP-181 | Ale Circle Realignment | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Construction | This is a combined projects: EP-181, EP-182 and EP-326 EP-181 $200,000 EP- 182 $550,000 EP-326 $1,100,000 Total project cost $1,850,000 | Construction 57 | Lowe Engineers | June, 2021 | August, 2021 | January, 2025 | December, 2024 |  | Sales Tax | $2,000,000 | $200,000 | $1,800,000 | Red | Yellow | Active | chall@eastpointcity.org | 2019 | 2024-11-07 14:48:16
[17 empty] | SUM = 2,000,000 | SUM = 200,000 | SUM = 1,800,000