## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 14 | EP-182 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Land | Operations and Safety in City of East Point - Ale Circle at Washington Road Intersection Improvements This project is a combined solicitation EP-181, EP182 and EP-326 Project total 1,850,000 EP-181 $200,000 EP-182 $550,000 EP 326 $1,100,000 | [7 empty] | Sales Tax | $550,000 | $100,000 | $450,000 | Green | Red | Active | JREEVES@EASTPOINTCITY.ORG | 2019 | 2021-02-01 23:59:28
[17 empty] | SUM = 550,000 | SUM = 100,000 | SUM = 450,000