## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 5 | 18-002 | Oakley Industrial Boulevard Full-Depth Reclamation (FDR) Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Completed | Full-Depth Reclamation of Oakley Industrial Boulevard, from Bohannon Road to just west of SR 74/ Senoia Road. The project also included asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. The approved T-SPLOST Project List allocates $897,309 of Roadway Projects funding to the Full-Depth Reclamation of Oakley Industrial Boulevard (OIB). Since we only did approximately half of the entire project, only $448,654.50 of TSPLOST Funds were allocated to the project.. | C.W.Matthews Contracting Co., Inc. | Moreland Altobelli Associates, LLC | May, 2018 | July, 2018 | February, 2019 | January, 2019 |  | Sales Tax | $629,879 | $411,049 | $218,830 | Green | Green | Active | lthompson@fairburn.com | 2018 | 2021-09-08 19:22:03
[17 empty] | SUM = 629,879 | SUM = 411,049 | SUM = 218,830