## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 6 | 18-002 | McLarin Road Full-Depth Reclamation Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | Full-Depth Reclamation of McLarin Road along with asphalt paving, the installation of thermoplastic striping and raised pavement markers (RPMs), and manhole and water valve adjustments. | C.W.Matthews Contracting Co., Inc. | Moreland Altobelli Associates, LLC | May, 2018 | July, 2018 | February, 2019 | January, 2019 |  | Sales Tax | $524,177 | $330,790 | $193,387 | Green | Green | Active | lthompson@fairburn.com | 2018
[17 empty] | SUM = 524,177 | SUM = 330,790 | SUM = 193,387