## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 10 |  | E. Broad Street & E. Malone Street Pedestrian Improvements Project | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | Fairburn | Completed | Pedestrian Improvements on E. Broad Street & E. Malone Street near Landmark Christain School. | BOSS Concrete | Design-Build | April, 2018 | August, 2018 | November, 2018 | October, 2018 |  | Sales Tax | $32,354 | $32,354 | $0 | Green | Green | Active | anthony.belcher@fairburn.com | 2018 | 2025-08-01 07:44:59 | GA | E. Broad St.
[17 empty] | SUM = 32,354 | SUM = 32,354 | SUM = 0