## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 11 | 18-011 | Renaissance Parkway Extension Project | Tier 3 | Congestion Relief | TSPLOST | Fairburn | Completed | Renaissance Parkway Roadway Extension Roadway project designed to provide congestiion relief to SR 74/Senoia Road. | AMCON Construction | Harris-Gray, LLC | August, 2018 | March, 2019 | December, 2019 | November, 2019 |  | Sales Tax | $87,611 | $87,611 | $0 | Green | Green | Active | lthompson@fairburn.com | 2019 | 2021-09-08 19:24:28
[17 empty] | SUM = 87,611 | SUM = 87,611 | SUM = 0