## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
PA- 3 | PA-111 | Operations and Safety- Phipps Rd/Fayetteville Rd Intersection | Tier 1 | Operation and Safety Improvements | TSPLOST | Palmetto | Planning | Operations and Safety in City of Palmetto Round-about for the intersection of Phipps Road and Fayetteville Road |  | Gresham Smith | December, 2020 | December, 2021 | June, 2022 |  |  | Sales Tax | $102,671 | $19,228 | $83,443 | Gray | Gray | Active | hanson@citypalmetto.com |  | 2021-05-04 15:37:27
[17 empty] | SUM = 102,671 | SUM = 19,228 | SUM = 83,443