## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
UC- 2 | UC-101 | Congestion Relief/Roadway Projects | Tier 1 | Congestion Relief | TSPLOST | Union City | Design | Congestion Relief in Union City - I-85/SR 138 Interchange (PARTIAL FUNDING) | TBD | WSP USA | August, 2023 | December, 2023 | December, 2025 | November, 2025 | http://www.dot.ga.gov | Sales Tax | $5,000,000 | $1,065,284 | $3,934,716 | Green | Red | Active | Lonnie Ferguson | 2026 | 2023-02-27 15:30:54
[17 empty] | SUM = 5,000,000 | SUM = 1,065,284 | SUM = 3,934,716