## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
UC- 4 | UC-103 | Operations and Safety | Tier 1 | Operation and Safety Improvements | TSPLOST | Union City | Completed | Operations and Safety in Union City - Flat Shoals Road Resurfacing and Streetscape Project (From Westbrook St to Oakley Rd) | Mullins Brothers Paving Contractors | Lowe Engineers | December, 2018 | April, 2019 | August, 2019 | April, 2020 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $418,624 | $995,318 | $-576,694 | Red | Green | Active | Lonnie Ferguson | 2020 | 2023-02-27 15:12:10
[17 empty] | SUM = 418,624 | SUM = 995,318 | SUM = -576,694