## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
UC- 9 | UC-108 | Pedestrian/Bike/Landscape/Streetscape | Tier 1 | Pedestrian and Bike Improvements | TSPLOST | Union City | Completed | Pedestrian/Bike/Landscape/Streetscape in Union City - Lower Dixie Lake Rd Sidewalks | Magnum Paving | Atlas | August, 2022 | September, 2022 | November, 2022 | December, 2022 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $203,500 | $904,300 | $-700,800 | Red | Green | Active | Lonnie Ferguson | 2022 | 2023-02-27 15:25:30
[17 empty] | SUM = 203,500 | SUM = 904,300 | SUM = -700,800