## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
UC- 10 | US-109 | Quick Response Projects | Tier 1 | Quick Response | TSPLOST | Union City | Completed | Quick Response Projects in Union City - Quick Response Projects | The Corbett Group | Atlas | March, 2019 | April, 2019 | August, 2019 | August, 2019 | https://www.unioncityga.org/departments/public-services/capital-projects | Sales Tax | $235,687 | $107,077 | $128,610 | Green | Green | Active | Lonnie Ferguson |  | 2023-02-27 15:31:46
[17 empty] | SUM = 235,687 | SUM = 107,077 | SUM = 128,610