## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 4 | CH-201 | Maintenance and Safety Enhancements | Tier 2 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Completed | The project consists of ôdeep patchingö (mill & inlay) repair of various roads as outlined in the bid packet. All milling quantities are based on the use of a 4Æ wide milling head. All patching asphalt quantities are based on an average depth of 3.5ö of asphalt binder. Precise locations have not been determined but will be marked in conjunction with Contractor prior to commencement of actual work. The tonnage shown for each road is an estimate and may be adjusted as required to match field conditions. | Blount Construction | DW Smith | June, 2019 | September, 2019 | October, 2019 | October, 2019 |  | Sales Tax ($365,000 TSPLOST/$52,8836 Capital Fund) | $418,322 | $417,836 | $486 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2018-2019 | 2021-12-13 18:30:13
[17 empty] | SUM = 418,322 | SUM = 417,836 | SUM = 486