## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
CH- 5 | CH-202 | Maintenance and Safety Enhancements | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Chattahoochee Hills | Construction | This project consists of deep patching South Fulton Parkway at the bridge/County line, Two locations on Campbellton-Redwine (approx. 1,000 lf), Cochran Mill @ Woodruff, Rivertown @ Campbellton-Redwine, Complete work begun on Rivertown, Hutcheson Ferry (approx. 1,000 lf). Crack sealing South Fulton Parkway (areas not addressed by GDOT), Hutcheson Ferry (from The Inn to Cochran Mill), Campbellton-Redwine, and striping South Fulton Parkway, Hutcheson Ferry, Rico Road (southern portion), Cochran Mill Road, Rivertown Road and Campbellton-Redwine | ER Snell | DWS | August, 2021 | September, 2021 | November, 2021 | December, 2021 | www.chatthillsga.us | Sales Tax | $1,251,765 | $1,211,895 | $39,870 | Green | Green | Active | robbie.rokovitz@chatthillsga.us | 2021 | 2021-12-13 18:29:16
[17 empty] | SUM = 1,251,765 | SUM = 1,211,895 | SUM = 39,870