## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 19 | EP-215 | Pedestrian/Bike Projects | Tier 2 | Pedestrian and Bike Improvements | TSPLOST | East Point | Land | Pedestrian/Bike Projects in City of East Point - Redwine Road (City of Atlanta to North Commerce Drive) This is a combined project EP-215 and EP-325 EP-215 $218,000 EP- 325 $350,000 Total project cost $568,000 |  |  | February, 2020 | August, 2021 | April, 2022 | December, 2021 |  | Sales Tax | $218,000 | $22,132 | $195,868 | Green | Yellow | Active | JREEVES@EASTPOINTCITY.ORG | 2020 | 2021-02-01 23:51:26
[17 empty] | SUM = 218,000 | SUM = 22,132 | SUM = 195,868