## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 20 | EP-216 | Ben Hill Rd (South) Sidewalks and Traffic Calming | Tier 1 | Operation and Safety Improvements | TSPLOST | East Point | Construction | Ben Hill Road (Will Lee Road to Unincorporated Fulton County) Traffic Calming and sidewalks | Sol Construction, LLC | Southeastern Engineers | June, 2021 | October, 2021 | February, 2022 | February, 2022 | www.eastpointcity.org | Sales Tax | $712,500 | $441,074 | $271,426 | Green | Green | Active | guest | 2021 | 2021-10-11 22:23:41
[17 empty] | SUM = 712,500 | SUM = 441,074 | SUM = 271,426