## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 5 | MIL-031 | Morris Road Widening | Tier 1 | Congestion Relief | TSPLOST | Milton | Construction | The overall project description is for a proposed widening from Webb Road to Bethany Bend tying into McGinnis Ferry Road widening at Bethany Bend. The cross section is proposed as a 4 lane divided roadway with landscaped median/turn lanes and multiuse trail including intersection improvements at Webb Road. |  | Pond & Company | September, 2023 | July, 2017 | August, 2026 | August, 2026 | https://cleargov.com/georgia/fulton/city/milton/projects/1212/morris-road-improvements-_-tsplost | Sales Tax | $10,363,837 | $972,739 | $9,391,098 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:11:19
[17 empty] | SUM = 10,363,837 | SUM = 972,739 | SUM = 9,391,098