## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 6 | MIL-001 | Hopewell Road at Bethany Bend/Way Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Operational improvements that will address the intersections of Hopewell Rd with Bethany Bend, Bethany Oaks Pointe, and Bethany Way and may include turn lanes, traffic signals or roundabouts | Vertical Earth | Pond & Company | March, 2021 | July, 2017 | March, 2023 | April, 2023 | https://cleargov.com/georgia/fulton/city/milton/projects/1210/hopewell-road-at-bethany-bend_or_bethany-way-_-tsplost | Sales Tax | $4,100,000 | $3,315,108 | $784,892 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:11:48
[17 empty] | SUM = 4,100,000 | SUM = 3,315,108 | SUM = 784,892