## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 8 | MIL-005/MIL-030 | Northeast Crabapple Connector Road | Tier 1 | Congestion Relief | TSPLOST | Milton | Completed | New alignment roadway from proposed improved intersection at Mayfield Rd and Charlotte Dr (Project MIL-005) to roundabout at SR 372/ Birmingham Hwy at McFarlin Ln | CMES | Pond & Company | October, 2018 | July, 2017 | February, 2021 | March, 2021 | http://miltonintersectionprojects.com/northeast-crabapple-connector-road/ | Sales Tax | $7,199,218 | $3,100,860 | $4,098,358 | Green | Green | Active | guest |  | 2021-09-30 18:26:57
[17 empty] | SUM = 7,199,218 | SUM = 3,100,860 | SUM = 4,098,358