## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 9 | MIL-006 | Hopewell Road at Thompson Road/South Thompson Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | Realignment of offset intersections and operational improvements that may include turn lanes, traffic signal, or roundabout | CMES | Barge Design Solutions | August, 2020 | February, 2018 | November, 2021 | October, 2021 | https://cleargov.com/georgia/fulton/city/milton/projects/1180/hopewell-road-at-thompson-road-_-tsplost | Sales Tax | $3,580,000 | $2,606,130 | $973,870 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:12:39
[17 empty] | SUM = 3,580,000 | SUM = 2,606,130 | SUM = 973,870