## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 12 | MIL-012 | Birmingham Road Middle Bridge | Tier 1 | Bridges | TSPLOST | Milton | Land | Bridge replacement with future trail accommodations |  | BM&K | August, 2026 | May, 2021 | October, 2027 | October, 2027 | https://cleargov.com/georgia/fulton/city/milton/projects/1217/birmingham-road-middle-bridge-_-tsplost | Sales Tax | $2,803,458 | $109,476 | $2,693,982 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:03:33
[17 empty] | SUM = 2,803,458 | SUM = 109,476 | SUM = 2,693,982