## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 14 | 20-002 | Roadway Improvements on Various City Roads Project | Tier 1 | Maintenance and Safety Enhancements | TSPLOST | Fairburn | Completed | 2020 City-Wide Resurfacing, Roadway Improvements Project | C.W.Matthews | In-House | March, 2020 | July, 2020 | December, 2020 | November, 2020 |  | Sales Tax | $1,157,670 | $694,620 | $463,050 | Green | Green | Active | lthompson@fairburn.com | 2020 | 2020-12-17 20:18:13
[17 empty] | SUM = 1,157,670 | SUM = 694,620 | SUM = 463,050