## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 14 | MIL-002 | Bethany Road at Providence Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Bidding | Operational improvements that will address the all way stop controlled intersection and may include turn lanes, traffic signal or roundabout |  | KCI | February, 2026 | April, 2021 | November, 2027 | November, 2027 | https://cleargov.com/georgia/fulton/city/milton/projects/1194/bethany-road-at-providence-road-_-tsplost | Sales Tax | $2,200,000 | $146,350 | $2,053,650 | Green | Green | Active | kathy.stallard@miltonga.gov |  | 2026-02-27 09:06:53
[17 empty] | SUM = 2,200,000 | SUM = 146,350 | SUM = 2,053,650