## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
UC- 16 | UC-206 | Quick Response Projects | Tier 3 | Quick Response | TSPLOST | Union City | Design | Quick Response Projects in Union City - Quick Response Projects | TBD | Atlas | April, 2021 | August, 2021 | February, 2023 | March, 2023 |  | Sales Tax | $235,686 | $0 | $235,686 | Red | Green | Active | lferguson@unioncityga.org | 2022 | 2021-02-02 19:53:06
[17 empty] | SUM = 235,686 | SUM = 0 | SUM = 235,686