## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
EP- 23 | EP-325 | Operations and Safety | Tier 3 | Operation and Safety Improvements | TSPLOST | East Point | Land | Operations and Safety in City of East Point - North Commerce Drive at Redwine Road Intersection Improvements Construction. This is a combined project EP-215 and EP-325 EP-215 $218,000 EP- 325 $350,000 Total project cost $568,000 |  |  | April, 2021 | October, 2021 | February, 2022 | January, 2022 |  | Sales Tax | $350,000 | $50,000 | $300,000 | Green | Red | Active | JREEVES@EASTPOINTCITY.ORG | 2019 | 2021-02-02 00:00:09
[17 empty] | SUM = 350,000 | SUM = 50,000 | SUM = 300,000