## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FA- 17 | 23-003 | Rivertown Connector Project | Tier 1 | Roadway Projects | TSPLOST | Fairburn | Bidding | City of Fairburn Roadway Project design to provide connectivity between Rivertown Road and Virlyn B. Smith Road. |  | SOUTHEASTERN ENGINEERING INC. | April, 2025 | May, 2025 | August, 2025 | July, 2025 |  | Sales Tax | $937,240 | $0 | $937,240 | Gray | Gray | Active | anthony.belcher@fairburn.com | 2020 | 2025-05-01 11:30:19
[17 empty] | SUM = 937,240 | SUM = 0 | SUM = 937,240