## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 9 | JCR-009 | Barnwell Road at Holcomb Bridge Road Intersection Improvements | Tier 1 | Operation and Safety Improvements | TSPLOST | Johns Creek | Construction | This project includes dual left turn lanes, a through lane, and a right-turn lane on Barnwell Road at SR 140/Holcomb Bridge Road. This project may include improvements including bike lanes, sidewalks, trails, landscaping and a pedestrian bridge over Hogan's Creek. | CW Matthews | DPE | December, 2019 | May, 2021 | July, 2023 | June, 2023 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Barnwell-Rd-at-Holcomb-Bridge-Rd-Intersection-Impr | Federal/State and Local | $2,500,000 | $1,674,213 | $825,787 | Green | Green | Active | chris.haggard@johnscreekga.gov |  | 2022-08-22 15:09:25
[17 empty] | SUM = 2,500,000 | SUM = 1,674,213 | SUM = 825,787