## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
JCR- 14 | JCR-019 | Barnwell Road Corridor Improvements | Tier 3 | Operation and Safety Improvements | TSPLOST | Johns Creek | Design | This project will include improvements along Barnwell Road which may include trails, sidewalks, bike lanes, turn lanes, roundabouts and landscaping. This overall project will be constructed as several smaller projects. | Williams Contracting | Michael Baker |  |  | November, 2022 | October, 2022 | https://www.johnscreekga.gov/Residents/Public-Works/TSPLOST/Barnwell-Road-Corridor-Improvements | Sales Tax | $2,046,245 | $2,046,245 | $0 | Green | Green | Active | kevin.albi@johnscreekga.gov |  | 2024-07-09 14:59:52 | Georgia | City of Johns Creek
[17 empty] | SUM = 2,046,245 | SUM = 2,046,245 | SUM = 0