## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
FIB- 27 | FFA 1001 | Charlie Brown Airport Matching Funds | Tier 1 | Fulton County Airport Improvements | TSPLOST | Fulton Industrial Blvd. | Planning | Matching Funds for federal and state grant programs for capital improvements at the Fulton County Airport | TBD | Michael Baker International | May, 2020 | May, 2020 | October, 2023 | July, 2023 |  | Sales Tax | $1,000,000 | $0 | $1,000,000 | Green | Green | Active | cordell.rhymer@fultoncountyga.gov | 2020
[17 empty] | SUM = 1,000,000 | SUM = 0 | SUM = 1,000,000