## Worksheet
Project ID | Local ID | Project Name Title | Tier | Project Type | Initiatve Type | City | Current Stage | Project Description | Construction Firm Selected | Design Firm Selected | Estimated Design Completion Date | Estimated Start Date For Project | Estimated Construction Completion Date | Estimated Substantial Completion Date | Link To External Website | Primary Funding Source | TSPLOST Budget ($) | TSPLOST Dollars Spent ($) | TSPLOST Dollars Committed (not spent) ($) | Cost Status | Schedule Status | Status | Editor | Project Year | Last Update | State | Address | Creation Date
MIL- 21 | MIL-031 (Interim) | Morris Road at Webb Road Roundabout (Interim Improvement Before Widening) | Tier 1 | Operation and Safety Improvements | TSPLOST | Milton | Completed | The overall project description is for a proposed widening from Webb Road to Bethany Bend tying into McGinnis Ferry Road widening at Bethany Bend. With recent signal improvements at Bethany Bend and Morris Road/McGinnis Ferry Road and upcoming interchange addition at GA 400 and McGinnis Ferry Road, an interim intersection improvement project was designed for the existing four way stop controlled intersection of Morris Road at Webb Road. Much of the project uses existing intersection footprint and converts the stop controlled intersection into a roundabout. The project will allow for future expansion with the upcoming widening project. | CMES | BM&K | March, 2018 | January, 2018 | October, 2018 | October, 2018 | https://cleargov.com/georgia/fulton/city/milton/projects/1212/morris-road-improvements-_-tsplost | Sales Tax | $400,000 | $363,289 | $36,711 | Green | Green | Active | sara.leaders@cityofmiltonga.us |  | 2021-04-29 21:48:52
[17 empty] | SUM = 400,000 | SUM = 363,289 | SUM = 36,711